**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 1 | | **Start date or starting event:** | | | | 01.12.2017. | | |
| **Work package title** | Acquiring information | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 3 | |  |  |  | |  |  |
| **Participant short name** | ND | AB | |  |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.1 | |  |  |  | |  |  |

|  |
| --- |
| **Objectives**  Interviewing potential customers, as well as people who already own a robot cleaner. Gathering their opinions on improving the existing robot cleaner or what they would like to see in our product. |

|  |
| --- |
| **Description of work**  Creating a detailed survey that will help gather the appropriate information.  Spreading the survey – either online or house-to-house.  Collecting the information and processing it.  ND and AB will work together in order to create the survey and process the information. AB will interview people face-to-face, while ND will take care of the online survey. |

|  |
| --- |
| **Deliverables**  Gathered information – this is the first deliverable of our project. It represents the information we’ve gathered from our potential customers. We plan to have it in a week – so in the first month of our project. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 2 | | **Start date or starting event:** | | | | 14.12.2017. | | |
| **Work package title** | Creating the prototype | | | | | | | | |
| **Activity type** | DEM | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.2 | | 0.1 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Creating a prototype which will possess all basic functionalities. This prototype will be able to scan the area, clean it and return to its charging station without any trouble. These are the functionalities essential to the SRHC, and they need to work properly. |

|  |
| --- |
| **Description of work**  Implementing sensors, that the SRHC is going to use in order to identify its surroundings.  Implementing the AI algorithms, that are going to help SRHC avoid obstacles.  Gathering the essential (possibly cheap, low quality) materials that the prototype is going to be built from.  Building the prototype and adding the software chip.  ND and SS will be working on the AI algorithms and sensors, considering the fact that those two tasks are tightly connected to each other. AB will be in charge of calculating the adequate parameters for the AI algorithms, as well as acquiring the needed materials. The team will work together in putting the SRHC prototype together. |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery  Prototype – one of the most important deliverables of the early stages of our project. It will be further tested and, after fixing the issues that might arise, it will work as a base for the upgrades we and our customers have in mind. We want the prototype to be done in the first month of the project. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 3 | | **Start date or starting event:** | | | | 14.12.2017. | | |
| **Work package title** | Finding the flaws | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.1 | | 0.2 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Finding all issues with the basic functionalities that could stall the development of higher level ones. |

|  |
| --- |
| **Description of work**  During the creation of the prototype, we will be thoroughly testing each phase. All issues are going to be tracked and labelled for fixing in the following steps.  AB will have the lead here, conducting the tests and labelling the issues. She will cooperate with ND and SS, letting them know if there are any major flaws that need to be fixed urgently or just gathering information from them about the implementations. |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery  List of flaws/bugs – after the testing, we will have a list of all bugs that appeared during the tests. It will be properly organized, each bug will have its priority level and an assignee that will be fixing it. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 4 | | **Start date or starting event:** | | | | 26.12.2017. | | |
| **Work package title** | Fixing the flaws | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.2 | | 0.1 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Fixing the flaws found in the previous step so the production could proceed. |

|  |
| --- |
| **Description of work**  ND and SS will be working on improving the algorithms they implemented, that caused the bugs. AB will be working on fixing parameters that were potentially off. Also, AB will conduct final testing in order for work to proceed. |

|  |
| --- |
| **Deliverables**  Working base –we will have a base model that will be fully functional. All the basic functionalities will have been implemented and tested at this point. The base model will further be improved by higher quality materials and functionalities. This is the deliverable we expect to be the last of the first month. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 5 | | **Start date or starting event:** | | | | 03.01.2018. | | |
| **Work package title** | Implementing components | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.3 | | 0.1 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Implementing the higher quality components, so the SRHC doesn’t break easily, doesn’t overheat, processes information it gathers faster and so on. |

|  |
| --- |
| **Description of work**  Acquiring high quality components.  Putting them to work.  SS will be in charge of this phase. He will do most of the work, with ND supporting him along the way. AB will do the research in order to find the best components for the SRHC. |

|  |
| --- |
| **Deliverables**  Prototype of improved quality – we will get a prototype with high quality components, that will allow it to work more efficiently. We expect to get this prototype in the second month of our project. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 6 | | **Start date or starting event:** | | | | 03.01.2018. | | |
| **Work package title** | Implementing functionality | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.3 | | 0.1 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Implementing higher functionalities that will allow the SRHC to access some hard-to-reach areas (like corners), recognize that its garbage bag is full and empty it, realize its battery is running low and return to the charging station in time and so on. |

|  |
| --- |
| **Description of work**  SS will be in charge of this part, cooperating with ND in advance algorithm implementation. Considering the fact there will be AI algorithms implemented, AB will work on finding the most fitting parameters for them. |

|  |
| --- |
| **Deliverables**  Highly functional product – this phase leaves us with a product of high functionality, able to do all the things we and our customers intended for it to do. We expect it in month 2 of our project. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 7 | | **Start date or starting event:** | | | | 18.01.2018. | | |
| **Work package title** | Overall testing | | | | | | | | |
| **Activity type** | DEM | | | | | | | | |
| **Participant number** | 1 | 3 | |  |  |  | |  |  |
| **Participant short name** | ND | AB | |  |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.2 | |  |  |  | |  |  |

|  |
| --- |
| **Objectives**  Testing the (final) product we got in the last step, making sure that everything works as planned. |

|  |
| --- |
| **Description of work** (possibly broken down into tasks) and role of partners  AB will be in charge of creating and conducting the tests, with ND assisting her in the process. The information gathered from the tests will then be processed by AB and ND will do the necessary fixes. |

|  |
| --- |
| **Deliverables**  Properly tested product – final version of the product, thoroughly tested and with all bugs fixed. The version that will be released to public in the next step. We expect it by the end of month 2. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 8 | | **Start date or starting event:** | | | | 26.01.2017. | | |
| **Work package title** | Release | | | | | | | | |
| **Activity type** | DEM | | | | | | | | |
| **Participant number** | 1 | 2 | |  |  |  | |  |  |
| **Participant short name** | ND | SS | |  |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.1 | |  |  |  | |  |  |

|  |
| --- |
| **Objectives**  Releasing the finished product, making it available to public for purchase. |

|  |
| --- |
| **Description of work**  ND will make deals with tech companies that will be selling our product.  SS will help ND in answering technical questions that might arise. |

|  |
| --- |
| **Deliverables**  Released product – fully functional, fully tested product that is released to public and is up for sale. We expect it by the very end of month 2. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 9 | | **Start date or starting event:** | | | | 26.01.2018. | | |
| **Work package title** | Marketing | | | | | | | | |
| **Activity type** | DEM | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.6 | 0.1 | | 0.3 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Conduct dissemination – spread word of SRHC and all things it can do. |

|  |
| --- |
| **Description of work**  ND will be in charge of this part, developing marketing techniques, creating advertisements together with AB and spreading them around. While SS will work as a ‘customer service’ for a few weeks after the release, answering all technical questions. |

|  |
| --- |
| **Deliverables**  / |