**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 1 | | **Start date or starting event:** | | | | 01.12.2017. | | |
| **Work package title** | Acquiring information | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 3 | |  |  |  | |  |  |
| **Participant short name** | ND | AB | |  |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.1 | |  |  |  | |  |  |

|  |
| --- |
| **Objectives**  Interviewing potential customers, as well as people who already own a robot cleaner. Gathering their opinions on improving the existing robot cleaner or what they would like to see in our product. |

|  |
| --- |
| **Description of work**  Creating a detailed survey that will help gather the appropriate information.  Spreading the survey – either online or house-to-house.  Collecting the information and processing it.  ND and AB will work together in order to create the survey and process the information. AB will interview people face-to-face, while ND will take care of the online survey. |

|  |
| --- |
| **Deliverables**  Gathered information – this is the first deliverable of our project. It represents the information we’ve gathered from our potential customers. We plan to have it in a week – so in the first month of our project. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 2 | | **Start date or starting event:** | | | | 14.12.2017. | | |
| **Work package title** | Creating the prototype | | | | | | | | |
| **Activity type** | DEM | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.2 | | 0.1 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Creating a prototype which will possess all basic functionalities. This prototype will be able to scan the area, clean it and return to its charging station without any trouble. These are the functionalities essential to the SRHC, and they need to work properly. |

|  |
| --- |
| **Description of work**  Implementing sensors, that the SRHC is going to use in order to identify its surroundings.  Implementing the AI algorithms, that are going to help SRHC avoid obstacles.  Gathering the essential (possibly cheap, low quality) materials that the prototype is going to be built from.  Building the prototype and adding the software chip.  ND and SS will be working on the AI algorithms and sensors, considering the fact that those two tasks are tightly connected to each other. AB will be in charge of calculating the adequate parameters for the AI algorithms, as well as acquiring the needed materials. The team will work together in putting the SRHC prototype together. |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery  Prototype – one of the most important deliverables of the early stages of our project. It will be further tested and, after fixing the issues that might arise, it will work as a base for the upgrades we and our customers have in mind. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 3 | | **Start date or starting event:** | | | | 14.12.2017. | | |
| **Work package title** | Finding the flaws | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.1 | | 0.2 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Finding all issues with the basic functionalities that could stall the development of higher level ones. |

|  |
| --- |
| **Description of work**  During the creation of the prototype, we will be thoroughly testing each faze. All issues are going to be tracked and labelled for fixing in the following steps.  AB will have the lead here, conducting the tests and labelling the issues. She will cooperate with ND and SS, letting them know if there are any major flaws that need to be fixed urgently or just gathering information from them about the implementations. |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery  List of flaws/bugs – after the testing, we will have a list of all bugs that appeared during the tests. It will be properly organized, each bug will have its priority level and an assignee that will be fixing it. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 4 | | **Start date or starting event:** | | | | 26.12.2017. | | |
| **Work package title** | Fixing the flaws | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** | 1 | 2 | | 3 |  |  | |  |  |
| **Participant short name** | ND | SS | | AB |  |  | |  |  |
| **Person-months per participant** | 0.1 | 0.2 | | 0.1 |  |  | |  |  |

|  |
| --- |
| **Objectives**  Fixing the flaws found in the previous step so the production could proceed. |

|  |
| --- |
| **Description of work**  ND and SS will be working on improving the algorithms they implemented, that caused the bugs. AB will be working on fixing parameters that were potentially off. Also, AB will conduct final testing in order for work to proceed. |

|  |
| --- |
| **Deliverables**  Working base –we will have a base model that will be fully functional. All the basic functionalities will have been implemented and tested at this point. The base model will further be improved by higher quality materials and functionalities. |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** | 5 | | **Start date or starting event:** | | | | 03.01.2017. | | |
| **Work package title** | Implementing components | | | | | | | | |
| **Activity type** | RTD | | | | | | | | |
| **Participant number** |  |  | |  |  |  | |  |  |
| **Participant short name** |  |  | |  |  |  | |  |  |
| **Person-months per participant** |  |  | |  |  |  | |  |  |

|  |
| --- |
| **Objectives** |

|  |
| --- |
| **Description of work** (possibly broken down into tasks) and role of partners |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** |  | | **Start date or starting event:** | | | |  | | |
| **Work package title** |  | | | | | | | | |
| **Activity type** |  | | | | | | | | |
| **Participant number** |  |  | |  |  |  | |  |  |
| **Participant short name** |  |  | |  |  |  | |  |  |
| **Person-months per participant** |  |  | |  |  |  | |  |  |

|  |
| --- |
| **Objectives** |

|  |
| --- |
| **Description of work** (possibly broken down into tasks) and role of partners |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** |  | | **Start date or starting event:** | | | |  | | |
| **Work package title** |  | | | | | | | | |
| **Activity type** |  | | | | | | | | |
| **Participant number** |  |  | |  |  |  | |  |  |
| **Participant short name** |  |  | |  |  |  | |  |  |
| **Person-months per participant** |  |  | |  |  |  | |  |  |

|  |
| --- |
| **Objectives** |

|  |
| --- |
| **Description of work** (possibly broken down into tasks) and role of partners |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** |  | | **Start date or starting event:** | | | |  | | |
| **Work package title** |  | | | | | | | | |
| **Activity type** |  | | | | | | | | |
| **Participant number** |  |  | |  |  |  | |  |  |
| **Participant short name** |  |  | |  |  |  | |  |  |
| **Person-months per participant** |  |  | |  |  |  | |  |  |

|  |
| --- |
| **Objectives** |

|  |
| --- |
| **Description of work** (possibly broken down into tasks) and role of partners |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery |

**Work package description**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package number** |  | | **Start date or starting event:** | | | |  | | |
| **Work package title** |  | | | | | | | | |
| **Activity type** |  | | | | | | | | |
| **Participant number** |  |  | |  |  |  | |  |  |
| **Participant short name** |  |  | |  |  |  | |  |  |
| **Person-months per participant** |  |  | |  |  |  | |  |  |

|  |
| --- |
| **Objectives** |

|  |
| --- |
| **Description of work** (possibly broken down into tasks) and role of partners |

|  |
| --- |
| **Deliverables** (brief description) and month of delivery |